## HardwareMatrix_20240731-222800
AndazAN8C - NPI 2024 Hardware Qualification Report
ID | Supplier | Component PM | Release Notes | Model/Vendor Part No. | HW | FW | Rev | RoHS/GreenSpec | Samples | Factory EOA | DCR/HFCN | A.Code | HP Part No. | Qual Status | Comments
AC Adapter
89237 - HP 65W Slim USB-C Straight AC Power Adapter Taroko II (Truly Linked Features: 64969)
583493 | AcBel (LB) | Wang, Joanna | Notes | ADL035-021G | A | 3CB3 |  |  |  |  | HFCN | TGJK | M52944-014 | Risk Release_Material | [5/20] Aligned with ODM that this source will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
583494 | Chicony (HH) | Wang, Joanna | Notes | A065RP72P-HW02 | A | 3EC0 |  |  |  |  | HFCN | TGJF | M52944-012 | Risk Release_Material | [5/20] Aligned with ODM that this source will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
583491 | Delta (4D) | Wang, Joanna | Notes | ADP-65UE BB | A | 9F19 |  |  |  |  | HFCN | TGJH | M52944-013 | Risk Release_Material | [5/20] Aligned with ODM that this source will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
583490 | Liteon | Wang, Joanna | Notes | PA-1650-28HG | A | 365A |  |  |  |  | HFCN | TGJE | M52944-011 | Risk Release_Material | [5/20] Aligned with ODM that this source will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
Battery
87774 - GD 59Whr Long Life Polymer Fast Charge 3 cell Battery (Truly Linked Features: 62021)
570307 | ATL (GG) | Hou, Sharon | Notes | PL;ATL448078,5.11Ah | 1.0 | 2 | ATL448078/Renesas |  |  |  | HFCN | TAJT | N66000-B71 | Risk Release_BOM | [7/5] [SIO2284580] Follow system team's direction that ODM will drop ATL battery from PV build to avoid blocking the PV build. Due to Qualcomm driver r5840 issue, ATL battery cannot successfully stop charging which impact on the Shipping Mode setting. Thi
570306 | COSMX | Hou, Sharon | Notes | PL;COSMX448078,5.11Ah | 1.0 | 5.05 | COSMX448078/TI |  |  |  | HFCN | TAJR | N66000-AC1 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
570315 | Dynapack | Hou, Sharon | Notes | PL;COSMX448078,5.11Ah | 1.0 | 5.05 | COSMX624266/TI |  |  |  | HFCN | TAJQ | N66000-2C1 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
570308 | Simplo | Hou, Sharon | Notes | PL;BYD448078,5.11Ah | 1.0 | 5.05 | BYD448078/TI |  |  |  | HFCN | TAHV | N66000-1E1 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
Camera
88356 - 24MRI DualAryMic MIPI-RAW 5MP Fixed IR WFOV Integrated Camera (Truly Linked Features: 63464)
612437 | Chicony | Hou, Sharon | Notes | CJFNE6720004330LH | A3 | NA | [5 empty] | TFHL | N76985-251 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
612436 | Luxvisions | Hou, Sharon | Notes | ACG501N3 | 2.1 | NA | [5 empty] | TRJK | N76985-651 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
Connector
79139 - USB Type C SMT CL-1.6mm STD 24P 30u' Au Connector qty1 (Truly Linked Features: 51305)
485967 | Lotes | Chen, Glan | Notes | AUSBA088-P003AC | X00 | NA |  | BFR/PVC | 2021-09-01 |  |  |  | M99046-L15 | Planning
485965 | Singatron | Chen, Glan | Notes | 2UB3C39-004111F | X00 | NA |  | BFR/PVC | 2021-09-01 |  |  |  | M99046-S15 | Planning
485966 | Suyin | Chen, Glan | Notes | 020090HB024G56BZL | X00 | NA |  | BFR/PVC | 2021-09-01 |  |  |  | M99046-Y15 | Planning
IC / Sensory / Controller
91580 - IC AUDIO AMP WSA8845 36 WLNSP (Truly Linked Features: 68885)
610105 | Qualcomm | Hung, Ting | Notes | WSA8845 | N/A | N/A | [6 empty] | P08380-001 | Risk Release_BOM | Change status to "Risk Release_BOM" for BOM set-up.
91581 - IC AUDIO CODEC WCD9385 60 FOWPSP (Truly Linked Features: 68886)
610102 | Qualcomm | Hung, Ting | Notes | WCD9385 | N/A | N/A | [6 empty] | P08381-001 | Risk Release_BOM | Change status to "Risk Release_BOM" for BOM set-up.
91606 - IC BATTERY CHGR 2360 62 MQFN (Truly Linked Features: 68964)
610247 | Qualcomm | Sabian Ho | Notes | SMB-2360-0-MQFN62-TR-02-0 | n/a | n/a | [6 empty] | P08338-001 | Risk Release_BOM | Change status to "Risk Release_BOM" for BOM set-up.
91597 - IC POL VREG PM8010-0-WLPSP20-TR-U40 20 WLPSP (Truly Linked Features: 68912)
610200 | Qualcomm | Sean Yang | Notes | PM8010-0-WLPSP20-TR-U40 | n/a | n/a | [6 empty] | P09501-001 | Risk Release_BOM | Change status to "Risk Release_BOM" for BOM set-up.
91582 - IC POL VREG PMC1010H-0-WLPSP80-TR-01002 80 WLPSP (Truly Linked Features: 68887)
610095 | Qualcomm | Sean Yang | Notes | PMC1010H-0-WLPSP80-TR-01002 | n/a | n/a | [6 empty] | P08336-001 | Risk Release_BOM | Change status to "Risk Release_BOM" for BOM set-up.
91734 - IC POL VREG PMC1010H-0-WLPSP80-TR-01006 80 WLPSP (Truly Linked Features: 69165)
612260 | Qualcomm | Sean Yang | Notes | PMC1010H-0-WLPSP80-TR-01006 | n/a | n/a | [6 empty] | P08336-002 | Risk Release_BOM | Change status to "Risk Release_BOM" for BOM set-up.
91587 - IC POL VREG PMC1011H-0-WLPSP80-TR-01001 80 WLPSP (Truly Linked Features: 68894)
610137 | Qualcomm | Sean Yang | Notes | PMC1011H-0-WLPSP80-TR-01001 | n/a | n/a | [6 empty] | P08341-001 | Risk Release_BOM | Change status to "Risk Release_BOM" for BOM set-up.
91736 - IC POL VREG PMKX-0101-0-FOWPSP42-TR-020 42 FOWPSP (Truly Linked Features: 69166)
612263 | Qualcomm | Sean Yang | Notes | PMKX-0101-0-FOWPSP42-TR-020 | n/a | n/a | [6 empty] | P10369-001 | Risk Release_BOM | Change status to "Risk Release_BOM" for BOM set-up.
91583 - IC PWR MGMT 8380 108 WLPSP (Truly Linked Features: 68888)
610135 | Qualcomm | Sabian Ho | Notes | PMC-8380-0-WLPSP108B-TR-01-0-0 | n/a | n/a | [6 empty] | P08340-001 | Risk Release_BOM | Change status to "Risk Release_BOM" for BOM set-up.
91584 - IC PWR MGMT 8380C 110 FOWPSP (Truly Linked Features: 68889)
610136 | Qualcomm | Sabian Ho | Notes | PMC-8380C-0-FOWPSP110B-TR-A2-0 | n/a | n/a | [6 empty] | P08339-001 | Risk Release_BOM | Change status to "Risk Release_BOM" for BOM set-up.
91585 - IC PWR MGMT 88380VE 104 WLPSP (Truly Linked Features: 68892)
610138 | Qualcomm | Sabian Ho | Notes | PMC-8380VE-0-WLPSP104-TR-01-0 | n/a | n/a | [6 empty] | P08342-001 | Risk Release_BOM | Change status to "Risk Release_BOM" for BOM set-up.
87354 - IC Redriver TUSB1002ARGER 24 VQFN (Truly Linked Features: 60198)
564558 | Texas Instruments | Hung, Ting | Notes | TUSB1002ARGER | NA | NA | [6 empty] | N61375-001 | Risk Release_BOM | Change status to "Risk Release_BOM" for BOM set-up.
89107 - IC Retimer PS8830QC 105 BGA (Truly Linked Features: 64851)
616933 | Parade | Hung, Ting | Notes | PS8830BGA105GTR-A4-QC0A02 | A4-QC0A02 | 530E | [6 empty] | N82940-002 | Risk Release_BOM | Change status to "Risk Release_BOM" for BOM set-up.
LCD Panel
91463 - 14.0 in 2.2K (2240 x 1400) BrightView UWVA WLED+LBL sRGB 100 300 DBCGP eDP 1.4+PSR2 60Hz flat VAZ LCD Panel (Truly Linked Features: 68633)
612105 | AUO (TR) | Lai, Joan | Notes | B140QAT01.1 | 0A | N/A | DC PID:B524 HH |  |  |  | HFCN | UDJP | P10303-3J1 | Risk Release_Material | [5/27] Aligned with ODM that its ETQ would be on 8/16 which is the same as the CFZ date.
612107 | BOE (0X/X6) | Lai, Joan | Notes | NV140DRM-N67 | V8.0 | N/A | DC PID:0D0A BOE |  |  |  | POR | UDJQ | P10303-LJ1 | Risk Release_Material | [5/27] Aligned with ODM that its ETQ would be on 8/16 which is the same as the CFZ date.
91462 - 14.0 in 2.2K (2240 x 1400) BrightView UWVA WLED+LBL sRGB 100 300 DBCGP eDP1.4 60Hz flat VAZ LCD Panel (Truly Linked Features: 68632)
612101 | AUO (TR) | Lai, Joan | Notes | B140QAT01.2 | 0A | N/A | DC PID:25B5 HH |  |  |  | DCR: | UDJL | P10302-3J1 | Dropped | [6/25] Based on the alignment email on 5/27, dropped this source from 25C1 Andaz/NPI2024 AndazAN8C since the SDL DBCG+(BOE) has panel crack issue in [MS04] testing.
612104 | BOE (0X/X6) | Lai, Joan | Notes | NV140DRM-N66 | V8.0 | N/A | DC PID:0D0B BOE |  |  |  | DCR: | UDJN | P10302-LJ1 | Dropped | [6/25] Based on the alignment email on 5/27, dropped this source from 25C1 Andaz/NPI2024 AndazAN8C since the SDL DBCG+(BOE) has panel crack issue in [MS04] testing.
89358 - 14.0 in 2.2K (2240 x 1400) BrightView UWVA WLED+LBL sRGB 100 300 DBTSP eDP 1.4+PSR2 Low-Power flat VAZ LCD Panel (Truly Linked Features: 65054)
584867 | AUO (TR) | Lai, Joan | Notes | B140QAT01.0 | 0A | N/A | FSV PID:CBAF HH |  |  |  | DCR: | MAPK | N85491-3J1 | Risk Release_Material | [7/7] Based on DCR#433722 to enable the DBTS+, aligned with ODM that AUO DBTS+ will go for in-cycle qual(PV offline). And its ETQ would be on 8/16(CFZ).
584870 | BOE (0X/X6) | Lai, Joan | Notes | NV140DRM-A60 | V8.1 | N/A | FSV PID:0C93 BOE | BFR/PVC |  |  | DCR: | MFFP | N85491-LJ1 | Risk Release_Material | [6/18] Based on DCR#433722 to enable the DBTS+ and its ETQ will align with 25C1 Andaz. ETQ would be on 8/16/2024 which is the same as the CFZ date.
Power Cords
50465 - C5 PWRCORD 1.0m stkr Premium AUST
247239 | Longwell | Wang, Joanna | Notes | PL8B7TLDA0AA033 | A | NA | A |  |  |  |  | GUSB | 213356-018 | Risk Release_Material | [5/20] Aligned with ODM that this source will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
50461 - C5 PWRCORD 1.0m stkr Premium DEN
247235 | Longwell | Wang, Joanna | Notes | PF8BFG4DA0AA033 | A | NA | A |  |  |  |  | GURQ | 213353-018 | Risk Release_Material | [5/20] Aligned with ODM that this source will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
50459 - C5 PWRCORD 1.0m stkr Premium EURO
402531 | Linetek | Wang, Joanna | Notes | M0A0661-205 | 2 | NA | 2 |  |  |  |  | JVVP | L03315-219 | Risk Release_Material | [5/20] Aligned with ODM that this source will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
247233 | Longwell | Wang, Joanna | Notes | PF8BFC7DA0AA033 | A | NA | A |  |  |  |  | GURA | L03315-019 | Risk Release_Material | [5/20] Aligned with ODM that this source will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
50470 - C5 PWRCORD 1.0m stkr Premium INDIA
247244 | Longwell | Wang, Joanna | Notes | PV8A8RADA0AA033 | A | NA | A |  |  |  |  | GURD | L03318-013 | Risk Release_Material | [5/20] Aligned with ODM that this source will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
50471 - C5 PWRCORD 1.0m stkr Premium JPN
247245 | Longwell | Wang, Joanna | Notes | PT8GTPYDM0AA033 | A | NA | A |  |  |  |  | GUSP | 349756-011 | Risk Release_Material | [5/20] Aligned with ODM that this source will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
50467 - C5 PWRCORD 1.0m stkr Premium KOR
247241 | Longwell | Wang, Joanna | Notes | PF8K4C7D80AA033 | A | NA | A |  |  |  |  | GUSF | 267836-013 | Risk Release_Material | [5/20] Aligned with ODM that this source will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
50456 - C5 PWRCORD 1.0m stkr Premium NA
402529 | Linetek | Wang, Joanna | Notes | F0A0661-203 | 3 | NA | 3 |  |  |  |  | JVVN | L03314-220 | Risk Release_Material | [5/20] Aligned with ODM that this source will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
247229 | Longwell | Wang, Joanna | Notes | PH8BNETD90AA033 | A | NA | A |  |  |  |  | GUQV | L03314-020 | Risk Release_Material | [5/20] Aligned with ODM that this source will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
50468 - C5 PWRCORD 1.0m stkr Premium PRC
247242 | Longwell | Wang, Joanna | Notes | P78B4TMD80AA033 | A | NA | A |  |  |  |  | GUZQ | 286497-018 | Risk Release_Material | [5/20] Aligned with ODM that this source will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
50463 - C5 PWRCORD 1.0m stkr Premium SWISS
247237 | Longwell | Wang, Joanna | Notes | PF8BFG6DA0AA033 | A | NA | A |  |  |  |  | GURU | 213354-018 | Risk Release_Material | [5/20] Aligned with ODM that this source will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
50466 - C5 PWRCORD 1.0m stkr Premium THAI
247240 | Longwell | Wang, Joanna | Notes | PF8BFETDA0AA033 | A | NA | A |  |  |  |  | GUZP | 285096-017 | Risk Release_Material | [5/20] Aligned with ODM that this source will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
50469 - C5 PWRCORD 1.0m stkr Premium TW (Truly Linked Features: 13440)
247243 | Longwell | Wang, Joanna | Notes | PT8Y8IGIT0AA033 | A | NA | A |  |  |  |  | GURB | L03316-012 | Dropped | [6/4] Dropped by DCR-lite from core team on 6/4/2024 and the source ID#279079 will replace its supply.
279079 | Longwell | Wang, Joanna | Notes | PT8Y8IGIT0AA033 | 2 | NA | 2 |  |  |  |  | GURB | L03316-012 | Risk Release_Material | [5/20] Aligned with ODM that this source will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
50460 - C5 PWRCORD 1.0m stkr Premium UK
402335 | Linetek | Wang, Joanna | Notes | P0A0661-205 | 1 | NA | 1 |  |  |  |  | JVVL | 213351-218 | Risk Release_Material | [5/20] Aligned with ODM that this source will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
247234 | Longwell | Wang, Joanna | Notes | PF8BFVHDA0AA033 | A | NA | 2 |  |  |  |  | GURF | 213351-018 | Risk Release_Material | [5/20] Aligned with ODM that this source will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
Processor
92768 - CPU Qualcomm Snapdragon X1P42100 3.40G 8C 16W Qualcomm - Purwa (Truly Linked Features: 70516)
620473 | Qualcomm | Chou, Alan | Notes | X1P-42100-1-NSP2127B-TR-00-0 | n/a | n/a | [6 empty] | P16415-001 | Risk Release_BOM
Solid State Drive
87918 - 1TB PCIe-4x4 2280 NVMe Three Layer Cell China Solid State Drive (Truly Linked Features: 62645,63014,63015,63016)
571719 | Kioxia | Cheng, Mark | Notes | KXG80ZNV1T02 | 1 | HP01AP40 | Gen4x4 |  |  |  |  | QFEE | N12388-001 | 2024-09-20 | [5/20] Aligned with ODM that this source will go for in-cycle OOC qual and ETQ would be on 9/20 which will catch up with the FCS date (9/20).
580580 | Samsung (A1) | Cheng, Mark | Notes | MZVL21T0HCLR-00BH1 | Rev0 | HPS4NGXH | Gen4x4 | BFR/PVC |  |  |  | TFLH | M10395-004 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
571556 | SK hynix | Cheng, Mark | Notes | HFS001TEJ9X101N | 0A | HPS1 | Gen4x4 | BFR/PVC |  |  |  | PZVV | N07861-001 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
582827 | Western Digital | Cheng, Mark | Notes | SDCPNRY-1T00-1006 | A | HPS3 | Gen4x4 |  |  |  | HFCN | TFMP | M54702-003 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
87915 - 512GB PCIe 2280 NVMe Value China Solid State Drive (Truly Linked Features: 62642,63456,69815)
612269 | Kioxia | Cheng, Mark | Notes | KBG60ZNV512G | 01 | HP02AX00 | Gen4x4 | BFR/PVC |  |  |  | THGR | N86403-001 | Risk Release_BOM | [7/8] Aligned with NPIMM that swap the Kioxia 512GB with SK Hynix 512GB, since the GPS material cannot support MV build. The ETQ for this source would be catch up with FCS (9/20).
593528 | Samsung (A1) | Cheng, Mark | Notes | MZVL8512HELU-00BH1 | Rev0 | HPS3NKXM | Gen4x4 | BFR/PVC |  |  | HFCN | SFRT | N52404-001 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
571541 | SK hynix | Cheng, Mark | Notes | HFS512GEJ9X108N | 0A | HPS2 | Gen4x4 | BFR/PVC |  |  |  | RGYA | N29137-001 | Risk Release_Material | [7/8] Aligned with NPIMM that swap the Kioxia 512GB with SK Hynix 512GB, since the GPS material cannot support MV build. This source will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
623484 | SK hynix | Cheng, Mark | Notes | HFS512GEM9X173N | 0A | HPS1 | Gen4x4 | BFR/PVC |  |  |  | TXRE | P06150-001 | OOC | [7/26] Core team added this new source on 7/23/2024. Aligned with ODM that the qualification will be arranged by OOC.
605680 | Western Digital | Cheng, Mark | Notes | SDEPNSJ-512G-1006 | A | HPS1N5A | Gen4x4 |  |  |  |  | TKRE | N94050-001 | Risk Release_BOM | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
87917 - 512GB PCIe-4x4 2280 NVMe Three Layer Cell China Solid State Drive (Truly Linked Features: 62644,63017,63018,63019)
571881 | Kioxia | Cheng, Mark | Notes | KXG80ZNV512G | 1 | HP01AP40 | Gen4x4 |  |  |  |  | QFED | N12387-001 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
580574 | Samsung (A1) | Cheng, Mark | Notes | MZVL2512HCJQ-00BH1 | Rev0 | HPS4NGXH | Gen4x4 | BFR/PVC |  |  |  | TFLF | M10394-004 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
571552 | SK hynix | Cheng, Mark | Notes | HFS512GEJ9X101N | 0A | HPS1 | Gen4x4 | BFR/PVC |  |  |  | PZVU | N07860-001 | 2024-09-20 | [5/20] Aligned with ODM that this source will go for in-cycle OOC qual and ETQ would be on 9/20 which will catch up with the FCS date (9/20).
582826 | Western Digital | Cheng, Mark | Notes | SDCPNRY-512G-1006 | A | HPS3 | Gen4x4 |  |  |  | HFCN | TFML | M54701-003 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
70733 - SSD 1TB 2280 PCIe-4x4 NVMe Three Layer Cell (Linked Features: 38694,45440,46429,51732,60297,70298)
532136 | Kioxia | Cheng, Mark | Notes | KXG80ZNV1T02 | 1 | HP01AP40 | Gen4x4 |  |  |  |  | QFEE | N12388-001 | 2024-09-20 | Will go for in-cycle OOC qual and ETQ would be on 9/20 which will catch up with the FCS date (9/20).
593518 | Micron | Cheng, Mark | Notes | MTFDKBA1T0TGD-1BK1AABHA | 1 | HPS0050 | Gen4x4 |  |  |  |  | TFRR | N78345-001 | 2024-09-20 | [5/20] Aligned with ODM that this source will go for in-cycle OOC qual and ETQ would be on 9/20 which will catch up with the FCS date (9/20).
580345 | Samsung (A1) | Cheng, Mark | Notes | MZVL21T0HCLR-00BH1 | Rev 0 | HPS4NGXH | Gen4x4 | BFR/PVC |  |  | HFCN | TFLH | M10395-004 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
503163 | SK hynix | Cheng, Mark | Notes | HFS001TEJ9X101N | 0A | HPS1 | Gen4x4 |  |  |  |  | PZVV | N07861-001 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
582489 | Western Digital | Cheng, Mark | Notes | SDCPNRY-1T00-1006 | A | HPS3 | Gen4x4 |  |  |  | HFCN | TFMP | M54702-003 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
47268 - SSD 512GB 2280 PCIe NVMe Value (Linked Features: 8847,46524,46526,52069,52070,52071)
610565 | Kioxia | Cheng, Mark | Notes | KBG60ZNV512G | 01 | HP02AX00 | Gen4x4 | BFR/PVC |  |  |  | THGR | N86403-001 | Risk Release_BOM | [7/8] Aligned with NPIMM that swap 512GB Kioxia with 512GB SK Hynix, since the GPS's material cannot support MV build. The ETQ for this source would be catch up with FCS.
615896 | Micron | Cheng, Mark | Notes | MTFDKBA512QGN-1BN1AABHA | 1 | HPSQ050 | Gen4x4 |  |  |  |  | TXHT | P05899-001 | OOC | [5/27] Core team added new source of Micron and full qualification is required. Sample ETA would be on 5/28.
593522 | Samsung (A1) | Cheng, Mark | Notes | MZVL8512HELU-00BH1 | Rev0 | HPS3NKXM | Gen4x4 | BFR/PVC |  |  | HFCN | SFRT | N52404-001 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
553933 | SK hynix | Cheng, Mark | Notes | HFS512GEJ9X108N | 0A | HPS2 | Gen4x4 |  |  |  | HFCN | RGYA | N29137-001 | Risk Release_Material | [7/8] Aligned with NPIMM that swap the Kioxia 512GB with SK Hynix 512GB, since the GPS's material cannot support MV build. Aligned with ODM that will pull in this source to catch up with CFZ(8/16).
623479 | SK hynix | Cheng, Mark | Notes | HFS512GEM9X173N | 0A | HPS1 | Gen4x4 | BFR/PVC |  |  |  | TXRE | P06150-001 | OOC | [7/26] Core team added this new source on 7/23/2024. Aligned with ODM that the qualification will be arranged by OOC.
605674 | Western Digital | Cheng, Mark | Notes | SDEPNSJ-512G-1006 | A | HPS1N5A | Gen4x4 |  |  |  |  | TKRE | N94050-001 | Risk Release_BOM | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
70732 - SSD 512GB 2280 PCIe-4x4 NVMe Three Layer Cell (Linked Features: 38692,45691,46522,51731,60294,70297)
532130 | Kioxia | Cheng, Mark | Notes | KXG80ZNV512G | 1 | HP01AP40 | Gen4x4 |  |  |  |  | QFED | N12387-001 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
593512 | Micron | Cheng, Mark | Notes | MTFDKBA512TGD-1BK1AABHA | 1 | HPS0050 | Gen4x4 |  |  |  |  | TFRQ | N78344-001 | 2024-09-20 | [5/20] Aligned with ODM that this source will go for in-cycle OOC qual and ETQ would be on 9/20 which will catch up with the FCS date (9/20).
580342 | Samsung (A1) | Cheng, Mark | Notes | MZVL2512HCJQ-00BH1 | Rev 0 | HPS4NGXH | Gen4x4 |  |  |  | HFCN | TFLF | M10394-004 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
503162 | SK hynix | Cheng, Mark | Notes | HFS512GEJ9X101N | 0A | HPS1 | Gen4x4 |  |  |  |  | PZVU | N07860-001 | 2024-09-20 | [5/20] Aligned with ODM that this source will go for in-cycle OOC qual and ETQ would be on 9/20 which will catch up with the FCS date (9/20).
582482 | Western Digital | Cheng, Mark | Notes | SDCPNRY-512G-1006 | A | HPS3 | Gen4x4 |  |  |  | HFCN | TFML | M54701-003 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
System Memory
89038 - 32Gb LPDDR5X 8533 0.5v IC FBGA315 (Truly Linked Features: 64721)
581537 | Micron (TF) | Cheng, Mark | Notes | MT62F1G32D2DS-023 WT:C | Y52P/C | 8533Mbps | 16Gb DDP | BFR/PVC |  |  |  | TGAA | N81479-691 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
605664 | Samsung (TH) | Cheng, Mark | Notes | K3KL8L80DM-MGCU | D | 8533Mbps | 16Gb DDP | BFR/PVC |  |  |  | TRJP | N81479-991 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
581535 | SK hynix | Cheng, Mark | Notes | H58G56BK8BX068 | CP(B) | 8533Mbps | 16Gb DDP | BFR/PVC |  |  |  | TFZR | N81479-391 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
90063 - 32Gb LPDDR5X 8533 0.5v IC FBGA315 China (Truly Linked Features: 67088)
607792 | Samsung (TH) | Cheng, Mark | Notes | K3KL8L80DM-MGCU | D | 8533Mbps | China | BFR/PVC |  |  |  | TRJP | N81479-991 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
594032 | SK hynix | Cheng, Mark | Notes | H58G56BK8BX068 | CP(B) | 8533Mbps | China | BFR/PVC |  |  |  | TFZR | N81479-391 | Risk Release_Material | Will go for in-cycle qual and ETQ would be on 8/16 which is same as the CFZ date.
Wireless LAN
92048 - WLAN Qualcomm Fast Connect WCN6856 Wi-Fi 6E +BT 5.3 WW (Truly Linked Features: 69729)
615136 | Foxconn | Chou, Timmy | Notes | NFA765A | NA | NA | [6 empty] | P10222-001 | Risk Release_BOM
92047 - WLAN Qualcomm Fast Connect WCN7851 Wi-Fi 7 +BT 5.4 WW (Linked Features: 69728)
615132 | Foxconn | Chou, Timmy | Notes | NCM865A | NA | NA | [6 empty] | P10221-001 | Risk Release_BOM