## HardwareMatrix_20240822-034953
Longhornz - NPI 2024 Hardware Qualification Report
ID | Supplier | Component PM | Release Notes | Model/Vendor Part No. | HW | FW | Rev | RoHS/GreenSpec | Samples | Factory EOA | DCR/HFCN | A.Code | HP Part No. | Qual Status | Comments
AC Adapter
77281 - HP 150W Slim 4.5 mm PFC Right Angle Smart (3-pin) AC Power Adapter Vesta II (Truly Linked Features: 49176)
501339 | Delta (4D) | Wang, Joanna | Notes | ADP-150YB BD | 0A | NA | 0A |  |  |  |  | MVYD | M85394-003 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
501340 | Lite-On (LL) | Wang, Joanna | Notes | PA-1151-08HP | A01 | NA | A01 |  |  |  |  | MVXQ | M85394-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
Battery
66131 - Battery MB 6 Cell WHr 83 Long Life -PL Fast Charge (Linked Features: 42121)
441113 | Simplo | Hou, Sharon | Notes | PL,685257Ah,3.58Ah,SMP/COS | 1/2 | 5.03 | 685257 |  |  |  | HFCN | LEYK | L77973-1C2 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
Camera
86947 - I5WR DualAryMic USB2 5MP Fixed IR WFOV Integrated Camera (Truly Linked Features: 59158)
559642 | Chicony | Hou, Sharon | Notes | CKFNE5421004330LH | A1 | TBC | B7E9 |  |  | Unavailable |  | SSAU | N58018-130 | Dropped | 01162024 : drop ID 559642 and replced by ID598769, they are the same, just add FW version.
598769 | Chicony | Hou, Sharon | Notes | CKFNE5421004330LH | A2 | 7 | B7E9 |  |  |  | HFCN | SSAU | N58018-130 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
628415 | Chicony | Hou, Sharon | Notes | CKFNE5421004331LH | A2 | 8 | VID 04F2 PID B7E9 |  |  |  |  | UJZH | N58018-131 | Investigating
598566 | Foxlink | Hou, Sharon | Notes | FO53FF-877H | TBC | TBC | [5 empty] | TPQF | N58018-230 | 09/08/2022 | test complete but align BIOS RTM schedule (8/30/2024) to push out .
628186 | Foxlink | Hou, Sharon | Notes | FO53FF-877H | A1 | 3 | VID 05C8 PID 0834 |  |  |  |  | TPQF | N58018-230 | Investigating
559640 | Luxvisions | Hou, Sharon | Notes | ABG505N3 | 2.0 | TBC | 00C1 |  |  | Unavailable |  | SSAV | N58018-370 | Dropped | 01162024 : drop ID 559640 and replced by ID598767, they are the same, just add FW version.
597841 | Luxvisions | Hou, Sharon | Notes | BBG502N3 | 2.0 | TBC | [5 empty] | TPJR | N58018-371 | 09/06/2024 | test complete but align BIOS RTM schedule (8/30/2024) to push out .
598767 | Luxvisions | Hou, Sharon | Notes | ABG505N3 | 2.0 | 7 | 00C1 |  |  | Unavailable | HFCN | SSAV | N58018-370 | QComplete | 01162024 test result is the same as ID559640 Align with CF on 3/1st/2024, RR on 1/25/2024.
628412 | Luxvisions | Hou, Sharon | Notes | ABG505N3A | 2.0 | 8 | VID 30C9 PID 00C1 |  |  |  |  | UJZF | N58018-372 | Investigating
628439 | Luxvisions | Hou, Sharon | Notes | BBG502N3 | 2.1 | 3 | VID 30C9 PID 00E1 |  |  |  | HFCN | TPJR | N58018-371 | Investigating
559645 | Rayprus | Hou, Sharon | Notes | HN2522 | 01 | TBC |  |  |  | Unavailable |  | SSBA | N58018-730 | Dropped | 01162024 : drop ID 559645 and replced by ID598770, they are the same, just add FW version.
598770 | Rayprus | Hou, Sharon | Notes | HN2522 | 04 | 7 | 1508 |  |  | Unavailable | HFCN | SSBA | N58018-730 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
559647 | TFC | Hou, Sharon | Notes | YHWG | A1 | TBC | 546A |  |  | Unavailable |  | SSAK | N58018-970 | Dropped | 01162024 : drop ID 559647 and replced by ID598771, they are the same, just add FW version.
597842 | TFC | Hou, Sharon | Notes | YHWG-1 | A1 | TBC | [5 empty] | TPJT | N58018-971 | 09/06/2024 | test complete but align BIOS RTM schedule (8/30/2024) to push out .
598771 | TFC | Hou, Sharon | Notes | YHWG | A2 | 8 | 546A |  |  | Unavailable | HFCN | SSAK | N58018-970 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
87740 - IFN DualAryMic FHD USB2 Fixed NFOV Integrated Camera (Truly Linked Features: 61893)
571187 | Chicony | Hou, Sharon | Notes | Â C7FNF2021004330LH | A1 | TBC | B804 |  |  | Unavailable |  | TAQP | N66501-1H0 | Dropped | Replaced by new ID to lock down HW/ FW ver.
604717 | Chicony | Hou, Sharon | Notes | Â C7FNF2021004330LH | A1 | 4 | B804 |  |  |  | HFCN | TAQP | N66501-1H0 | QComplete | New ID to lock down HW/FW ver. Qual result leveraged from old ID.
571190 | Luxvisions | Hou, Sharon | Notes | ASF211N3Â | 2.0 | TBC | 00D3 |  |  | Unavailable |  | TAQQ | N66501-3K0 | Dropped | Replaced by new ID to lock down HW/ FW ver.
604719 | Luxvisions | Hou, Sharon | Notes | ASF211N3Â | 2.0 | 5 | 00D3 |  |  |  | HFCN | TAQQ | N66501-3K0 | QComplete | New ID to lock down HW/FW ver. Qual result leveraged from old ID.
628406 | Luxvisions | Hou, Sharon | Notes | ASF211N3A | 2.0 | 6 | VID 30C9 PID00D3 |  |  |  | HFCN | UJZC | N66501-3K1 | Investigating
571186 | TFC | Hou, Sharon | Notes | Â YHI | A1 | TBC | 546D |  |  | Unavailable |  | TAQK | N66501-9G0 | Dropped | Replaced by new ID to lock down HW/ FW ver.
604716 | TFC | Hou, Sharon | Notes | Â YHI | A2 | 5 | 546D |  |  |  | HFCN | TAQK | N66501-9G0 | QComplete | New ID to lock down HW/FW ver. Qual result leveraged from old ID.
628405 | TFC | Hou, Sharon | Notes | Â YHI-1 | A2 | 6 | VID 0408 PID546D |  |  |  |  | UJZB | N66501-9G1 | Investigating
Connector
54905 - Connector DCin JCK ThruHole 4P STD CL3.0 Qty:1 L19209 (Linked Features: 63880)
279633 | Singatron | Chen, Glan | Notes | 2DC3071-039111F | X00 | NA |  | BFR/PVC | 12/14/2017 |  |  |  | L19209-S01 | Risk Release_BOM
279635 | Suyin | Chen, Glan | Notes | 040098HR002BA11ZL | X00 | NA |  | BFR/PVC | 12/14/2017 |  |  |  | L19209-Y01 | Risk Release_BOM
76776 - SODIMM DDR5 SMT H4.0mm REV 10u' Au Connector qty1 (Truly Linked Features: 48488,49057)
466281 | Argosy | Chen, Glan | Notes | D5AR0-26210-1P40H | X00 | NA |  | BFR/PVC | 04/20/2021 |  |  |  | M54483-AR5 | Risk Release_BOM
466283 | Daron | Chen, Glan | Notes | 567Y02-003H | X00 | NA |  | BFR/PVC | 04/22/2021 |  |  |  | M54483-DR5 | Risk Release_BOM
466279 | Foxconn | Chen, Glan | Notes | ASAAC26-J4RB0-7H | X00 | NA |  | BFR/PVC | 04/20/2021 |  |  |  | M54483-FR5 | Risk Release_BOM
466284 | Lotes | Chen, Glan | Notes | ADR50012-P003A03 | X00 | NA |  | BFR/PVC | 04/20/2021 |  |  |  | M54483-LR5 | Risk Release_BOM
75041 - SODIMM DDR5 SMT H4.0mm STD 10u' Au Connector qty1 (Truly Linked Features: 45726)
452473 | Argosy | Chen, Glan | Notes | D5AS0-26210-1P40H | X00 | NA |  | BFR/PVC | 01/15/2021 |  |  |  | M54482-AS5 | Risk Release_BOM
452474 | Daron | Chen, Glan | Notes | 567Y01-003H | X00 | NA |  | BFR/PVC | 01/14/2021 |  |  |  | M54482-DS5 | Risk Release_BOM
452472 | Foxconn | Chen, Glan | Notes | ASAAC26-J4SB0-7H | X00 | NA |  | BFR/PVC | 01/14/2021 |  |  |  | M54482-FS5 | Risk Release_BOM
452475 | Lotes | Chen, Glan | Notes | ADR50011-P003A03 | X00 | NA |  | BFR/PVC | 01/14/2021 |  |  |  | M54482-LS5 | Risk Release_BOM
78750 - USB 4.0 Type C SMT CL1.6mm STD 24P 30u' Au Connector qty1 (Truly Linked Features: 51099)
483671 | Foxconn | Chen, Glan | Notes | UT12113-1160Q-7H | X00 | NA |  | BFR/PVC | 08/17/2021 |  |  |  | M99047-F57 | OOC | Wait for Foxconn TID certification
483674 | Singatron | Chen, Glan | Notes | 2UB1793-C10111F | X00 | NA |  | BFR/PVC | 08/17/2021 |  |  |  | M99047-S57 | Risk Release_BOM
599864 | Suyin | Chen, Glan | Notes | 020090HB024G56SZL | X00 | NA | Y01 | BFR/PVC | 01/02/2024 | 01/10/2024 |  |  | M99047-Y58 | Risk Release_BOM
Docking Station
79770 - HP Thunderbolt 280W G4 Dock w/Combo Cable (Linked Features: 47968,47969,47970,47971,47972,47973,55268,55270)
493837 | Inventec | Hsiao, Ian | Notes | HP Thunderbolt Dock 280W G4 | Production | NPI-RTM | [7 empty] | Planning
Graphics Memory
87074 - GDDR6 512Mx32 1.1V 11Gbps Graphic Memory (Truly Linked Features: 59352)
559453 | Samsung (A1) | Shih, Vincent | Notes | K4ZAF325BC-SC16 | C | 1.1V 11Gbps |  | BFR/PVC |  | 12/30/2025 |  | MLYB | M30891-982 | Risk Release_BOM
76072 - GDDR6 512Mx32 1.35V 16Gbps Graphic Memory (Truly Linked Features: 47561)
461977 | Hynix (H1) | Shih, Vincent | Notes | H56G42AS4DX014 | DA(A) | 16Gbps |  | BFR/PVC | 07/14/2021 | 12/31/2023 |  | MLXV | M30891-381 | Risk Release_BOM
470083 | Micron | Shih, Vincent | Notes | MT61K512M32KPA-16:C | 1z C | 16Gbps |  | BFR/PVC | 07/30/2021 | 12/31/2023 |  | MLYA | M30891-681 | Risk Release_BOM
461975 | Samsung (A1) | Shih, Vincent | Notes | K4ZAF325BC-SC16 | C | 16Gbps |  | BFR/PVC | 07/14/2021 | 12/31/2023 |  | MLYB | M30891-982 | Risk Release_BOM
89052 - GDDR6 512Mx32 1.35V 16Gbps WN21-X7-S Graphic Memory (Truly Linked Features: 64782)
581631 | Samsung (A1) | Shih, Vincent | Notes | K4ZAF325BC-SC16 | C | 16Gbps |  | BFR/PVC |  | 12/31/2024 |  | MLYB | M30891-982 | Risk Release_BOM
581632 | SK hynix | Shih, Vincent | Notes | H56G42AS4DX014 | A | 16Gbps |  | BFR/PVC |  | 12/31/2024 |  | MLXV | M30891-381 | Risk Release_BOM
IC / Sensory / Controller
80003 - 12 LGA Accelerometer Sensor LIS2DW12 (Truly Linked Features: 52105)
496848 | STMicroelectronics | Chou, Alan | Notes | LIS2DW12TR | n/a | n/a | [6 empty] | N00490-001 | Risk Release_BOM
87455 - 6 LGA Ambient Light Sensor CM32181 (Truly Linked Features: 60340)
565881 | Vishay | Chou, Alan | Notes | CM32181 | n/a | n/a | [6 empty] | N50878-001 | Risk Release_BOM
76021 - IC AUDIO CODEC ALC3247-CG 40 QFN (Truly Linked Features: 47425)
459351 | REALTEK | Chou, Timmy | Notes | ALC3247-CGT | NA | NA | [6 empty] | 916899-001 | Risk Release_BOM
76312 - IC BATTERY CHGR BQ24800 28 WQFN (Truly Linked Features: 47892)
462193 | Texas Instruments | Linda Liu | Notes | BQ24800RUYR | BQ24800RUYR | N/A | [6 empty] | M59414-001 | Risk Release_BOM
77184 - IC CR RTS5258S-GR 32 QFN (Truly Linked Features: 49094)
469953 | REALTEK | Chou, Timmy | Notes | RTS5258S-GR | NA | NA | [6 empty] | 822265-001 | Risk Release_BOM
84573 - IC DRIVER MOS 5317U 31 QFN (Truly Linked Features: 56003)
530910 | AOS | Linda Liu | Notes | AOZ5317UQI | AOZ5317UQI | NA | [6 empty] | N27678-002 | Risk Release_BOM
84569 - IC DRIVER MOS 86901F 21 TQFN (Truly Linked Features: 56000)
530905 | Monolithic Power Systems | Linda Liu | Notes | MP86901-FGLT-C07M-Z | MP86901-FGLT-C07M-Z | NA | [6 empty] | N31402-001 | Risk Release_BOM
84570 - IC DRIVER MOS 86941D 21 TQFN (Truly Linked Features: 56001)
530907 | Monolithic Power Systems | Linda Liu | Notes | MP86941-DGQVT-C07M-Z | MP86941-DGQVT-C07M-Z | NA | [6 empty] | N05890-003 | Risk Release_BOM
80109 - IC DRIVER MOS 86959G 34 LGA (Truly Linked Features: 52195)
498018 | Monolithic Power Systems | Linda Liu | Notes | MP86959GMW-Z | MP86959GMW-Z | N/A | [6 empty] | N05891-001 | Risk Release_BOM
86659 - IC EC NPCX499HA0BX 144 BGA (Truly Linked Features: 58513)
553815 | Nuvoton | Chou, Alan | Notes | NPCX499HA0BX | n/a | n/a | [6 empty] | N35346-001 | Risk Release_BOM
91355 - IC EC NPCX499HA1BX 144 BGA (Truly Linked Features: 68475)
607195 | Nuvoton | Chou, Alan | Notes | NPCX499HA1BX | n/a | n/a | [6 empty] | P06384-001 | Planning | Bridge NPCX499HA1BX(Root: 91355/HPPN: P06384-001) to NPCX499HA0BX(RID: 86659/HPPN: N35346-001).
88091 - IC PWR MGMT 29000 56 TQFN (Truly Linked Features: 63032)
572526 | Monolithic Power Systems | Linda Liu | Notes | MP29000GQKT-9B00-Z | MP29000GQKT-9B00-Z | 9B00 | [6 empty] | N68860-001 | Risk Release_BOM
83932 - IC PWR MGMT 9529Q 20 WQFN (Truly Linked Features: 55388)
525538 | UPI | Linda Liu | Notes | UP9529QQKF | UP9529QQKF | NA | [6 empty] | N28006-001 | Risk Release_BOM
78260 - IC PWR SWITCH PI5USB2546 16 UQFN (Truly Linked Features: 50511)
479247 | Diodes | Ramirez, Juan | Notes | PI5USB2546ZHDEX-54 | PI5USB2546ZHDEX-54 | N/A | [6 empty] | M59407-002 | Risk Release_BOM | Bridge to TI TPS2546RTER (RID : 76315, HPPN : M59407-001).
76315 - IC PWR SWITCH TPS2546 16 WQFN (Truly Linked Features: 47895)
462210 | Texas Instruments | Ramirez, Juan | Notes | TPS2546RTER | TPS2546RTER | N/A | [6 empty] | M59407-001 | Risk Release_BOM
78291 - IC REDRIVER MUX 8719E 24 TQFN (Truly Linked Features: 50526)
479556 | Parade | Ramirez, Juan | Notes | PS8719ETQFN24GTR2-A0 | PS8719ETQFN24GTR2-A0 | N/A |  |  |  |  | DCR: |  | M64350-001 | Dropped | Remove Parade PS8719ETQFN24GTR2-A0 HPPN (M64350-001).
87970 - IC Redriver TUSB522PRGER 24 VQFN (Truly Linked Features: 62773)
571820 | Texas Instruments | Hung, Ting | Notes | TUSB522PRGER | TUSB522PRGER | N/A | [6 empty] | N66234-001 | Risk Release_BOM
80053 - IC Retimer 8409A C0 48 QFN (Truly Linked Features: 52129)
497142 | Parade | Ramirez, Juan | Notes | PS8409AQFN48GTR2-C0 | PS8409AQFN48GTR2-C0 | N/A | [6 empty] | M64347-002 | Risk Release_BOM
87499 - IC Smart Card Reader AK9563 28 TSSOP (Truly Linked Features: 60431)
566528 | Alcorlink | Chou, Alan | Notes | AK9563 | n/a | n/a | [6 empty] | N62712-001 | Risk Release_BOM
86213 - IC Thunderbolt Retimer Hayden Bridge JHL9040R (Truly Linked Features: 57895)
546601 | Intel | Fan, Leslie | Notes | JHL9040R | NA | NA | [6 empty] | N36941-001 | Risk Release_BOM
75420 - IC TPM 32 QFN (Truly Linked Features: 46088)
514107 | Nuvoton | Chou, Alan | Notes | NPCT760HABYX | n/a | 7.2.3.1 | [6 empty] | N21621-001 | Risk Release_BOM | Bridge to ST ST33HTPH2X32AHE4 (RID : 76950, HPPN : N36947-001).
599343 | Nuvoton | Chou, Alan | Notes | NPCT760HACYX | NPCT760HACYX | 7.2.4.0 | [6 empty] | N99602-001 | Investigating
76950 - IC TPM 32 VQFN (Truly Linked Features: 48656)
538637 | STMicroelectronics | Chou, Alan | Notes | ST33HTPH2X32AHE4 | n/a | 1.769 | [6 empty] | N36947-001 | Risk Release_BOM
89576 - IC USB Type-C Dual Port 5458H-01001 68 QFN (Truly Linked Features: 65455)
587850 | REALTEK | Cheng David | Notes | RTS5458H-01001 | NA | NA | [6 empty] | N23041-BI3 | Risk Release_BOM
84043 - NVIDIA GEFORCE RTX 4050 GN21-X2-K1 Graphics Controller (Linked Features: 55532)
526656 | Nvidia | Chen, George | Notes | GeForce RTX 4050 Laptop GPU | 00 | 0 | 0A | BFR/PVC |  |  | DCR: |  | N29051-001 | Risk Release_BOM | Final direction from ACS Exec Leadership is to DCR out GeForce for Power G11. (Based on mail sent by SM Barry on 8/30) 09/26/2023 : Change qual status to Planning due to DCR 414631.
88315 - NVIDIA RTX 1000 Ada WN21-X2-K2 Graphics Controller (Truly Linked Features: 63417)
575388 | Nvidia | Chen, George | Notes | AD107-950-K2-A1 | 00 | 0 | 0A | BFR/PVC |  |  |  |  | N70697-001 | Risk Release_BOM
85210 - NVIDIA RTX 2000 Ada WN21-X4 Graphics Controller (Truly Linked Features: 56902)
535820 | Nvidia | Chen, George | Notes | RTX 2000 | 00 | 0 | 0A | [5 empty] | N35087-001 | Risk Release_BOM
85211 - NVIDIA RTX 3000 Ada WN21-X7-S Graphics Controller (Truly Linked Features: 56903)
535821 | Nvidia | Chen, George | Notes | WN21-X7-S | 00 | 0 | 0A | [5 empty] | N35088-001 | Risk Release_BOM
88316 - NVIDIA RTX 500 Ada WN21-X1-B-KB Graphics Controller (Truly Linked Features: 63419)
575393 | Nvidia | Chen, George | Notes | AD107-925-KB-A1 | 00 | 0 | 0A | BFR/PVC |  |  |  |  | N70698-001 | Risk Release_BOM
LCD Monitor
87604 - HP Series 7 Pro37.5WQHD+ Thunderbolt 4 Monitor 7 38pu (Linked Features: 61765)
568662 | Wistron | Joy Lee | Notes | 738pu | A | 1 | [6 empty] | N56082-001 | Investigating
69747 - HP Z27k G3 4K Monitor (Truly Linked Features: 37501)
418389 | Wistron | JS Jou | Notes | TBD | EVT | EVT | [7 empty] | Investigating
69740 - HP Z27u G3 QHD USB-C Monitor (Truly Linked Features: 37500)
418384 | Wistron | JS Jou | Notes | TBD | EVT | EVT | [7 empty] | Investigating
89746 - OMEN Transcend 32UHD 240Hz OLED Gaming Monitor (Linked Features: 65722)
589206 | Wistron | David Chuang | Notes | OMEN Transcend 32 | A | 1 | [6 empty] | N86784-001 | Investigating
LCD Panel
86060 - 16.0 in WQXGA (2560 x 1600) Anti-Glare UWVA Low Blue Light sRGB 100 400 eDP 1.4+PSR2 120Hz (VRR) bent LCD Panel (Truly Linked Features: 57804)
545345 | AUO (TR) | Lai, Joan | Notes | B160QAN03.N | 0A | N/A | PID:A0A9 DC FSV VR | BFR/PVC | 02/17/2023 |  | HFCN | RVFV | N41333-361 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/26/2024 to 02/08/2024 support Sub revA.
545350 | BOE (0X/X6) | Lai, Joan | Notes | NE160QDM-NYG | V18.0 | N/A | PID: 0BBC DC FSV VR | BFR/PVC | 02/17/2023 |  | HFCN | RVGA | N41333-L61 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/26/2024 to 02/08/2024 support Sub revA.
87211 - 16.0 in WUXGA (1920 x 1200) Anti-Glare UWVA LED NTSC 45 NB2X 300 eDP 1.2 w/o PSR bent LCD Panel (Truly Linked Features: 59904)
566287 | AUO (TR) | Lai, Joan | Notes | B160UAN04.4 | 0A | N/A | DC FSV PID:FFAC | BFR/PVC | 07/14/2023 |  | HFCN | SWUL | N61960-361 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/26/2024 to 02/08/2024 support Sub revA.
566290 | BOE (0X/X6) | Lai, Joan | Notes | NV160WUM-N41 | V8.1 | N/A | DC FSV PID:0C31 | BFR/PVC | 07/14/2023 |  | HFCN | SWUV | N61960-L61 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/26/2024 to 02/08/2024 support Sub revA.
566291 | INX | Lai, Joan | Notes | N160JCA-EEK | C2 | N/A | DC FSV PID:1638 | BFR/PVC | 07/14/2023 |  | HFCN | SWUU | N61960-J61 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
566294 | LGD | Lai, Joan | Notes | LP160WU3 | SPD1 | N/A | DC FSV PID:078E | BFR/PVC | 07/14/2023 |  | HFCN | SXLP | N61960-261 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/26/2024 to 02/08/2024 support Sub revA.
87210 - 16.0 in WUXGA (1920 x 1200) Anti-Glare UWVA LED NTSC 45 NB2X 300 TOP eDP 1.2 w/o PSR bent LCD Panel (Truly Linked Features: 59903)
566308 | AUO (TR) | Lai, Joan | Notes | B160UAK01.3 | 0A | N/A | DC FSV PID:B0AC | BFR/PVC | 07/14/2023 |  | HFCN | SWUN | N61961-361 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/26/2024 to 02/08/2024 support Sub revA.
566316 | BOE (0X/X6) | Lai, Joan | Notes | NV160WUM-T01 | V8.1 | N/A | DC FSV PID:0C35 | BFR/PVC | 07/14/2023 |  | HFCN | SWVB | N61961-L61 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/26/2024 to 02/08/2024 support Sub revA.
566320 | INX | Lai, Joan | Notes | N160JCN-EEK | C2 | N/A | DC FSV PID:1639 | BFR/PVC | 07/14/2023 |  | HFCN | SWVA | N61961-J61 | Dropped | 03/01/2024 drop ID566320 (C2), due to CS fail on 400/600 G11. Replace by ID597944 ver C3.
597944 | INX | Lai, Joan | Notes | N160JCN-EEK | C3 | N/A | DC FSV PID:164A TS FW:6722T04 | BFR/PVC | 07/12/2023 |  | HFCN | TPHN | N61961-J62 | QComplete | NPI qual -J61 and PV offline qual -J62. QC based on sign off status.
75688 - 16.0 in WUXGA (1920 x 1200) Anti-Glare UWVA WLED+LBL sRGB 100 NB2Y 1000 eDP 1.3+PSR PrivacyG4 Plus bent LCD Panel (Truly Linked Features: 46566)
457500 | IVO | Lai, Joan | Notes | X160NV42 | R0 | NA | W |  |  |  | HFCN | MEGT | M74471-ND1 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/26/2024 to 02/08/2024 support Sub revA.
76512 - 16.0 in WUXGA (1920 x 1200) Anti-Glare UWVA WLED+LBL sRGB NB2Y 400 eDP 1.4+PSR2 Low-Power 100 bent LCD Panel (Truly Linked Features: 48178)
555305 | AUO (TR) | Lai, Joan | Notes | B160UAN01.L | 2A | NA | PID:10AB DC FSV | BFR/PVC | 03/14/2023 |  | HFCN | SLUD | M81328-362 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/26/2024 to 02/08/2024 support Sub revA.
616553 | AUO (TR) | Lai, Joan | Notes | B160UAN01.L | 6A | NA | PID:E8B3 DC FSV | BFR/PVC | 06/30/2024 |  | HFCN | UETQ | M81328-363 | Investigating
555304 | BOE (0X/X6) | Lai, Joan | Notes | NE160WUM-N63 | V8.1 | NA | PID:0BFB DC FSV | BFR/PVC | 04/14/2023 |  | HFCN | SLUF | M81328-L62 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/26/2024 to 02/08/2024 support Sub revA.
616554 | BOE (0X/X6) | Lai, Joan | Notes | NE160WUM-N63 | V8.2 | NA | PID:0CFC DC FSV | BFR/PVC | 06/30/2024 |  | HFCN | UETT | M81328-L63 | Investigating
555303 | INX | Lai, Joan | Notes | N160JCG-GT2 | C6 | NA | PID:1636 DC FSV | BFR/PVC | 06/27/2023 |  | HFCN | SLUE | M81328-J62 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/26/2024 to 02/08/2024 support Sub revA.
616556 | INX | Lai, Joan | Notes | N160JCG-GT2 | C9 | NA | PID:1657 DC FSV | BFR/PVC | 06/30/2024 |  | HFCN | UETR | M81328-J63 | Investigating
NFC Module
46678 - NFC Mirage WNC XRAV-1 (Linked Features: 8361)
214463 | WNC | Tan, Tony | Notes | XRAV-1 | NXP NPC300 | BETA | [5 empty] | GEPP | 914757-001 | Risk Release_BOM
Power Cords
75038 - C5 1.0m stkr Conventional Straight HF DEN PWRCORD
453787 | ISHENG | Wang, Joanna | Notes | M54452-401 | 1 | NA | 1 |  |  | Unavailable |  | LVSD | M54452-401 | Dropped | 12/15/2023 DCR-lite to drop more ISHENG HF power cord from non-QC platforms.
453786 | Linetek | Wang, Joanna | Notes | K0A0661-256(HP)N | 1 | NA | 1 |  |  |  |  | LUNP | M54452-201 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
453785 | Longwell | Wang, Joanna | Notes | 1151-0031 | 1 | NA | 1 |  |  |  |  | LUGP | M54452-101 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
75036 - C5 1.0m stkr Conventional Straight HF EURO PWRCORD (Truly Linked Features: 45724)
453900 | ISHENG | Wang, Joanna | Notes | M54454-401 | 1 | NA | 1 |  |  | Unavailable |  | LVSF | M54454-401 | Dropped | 12/13/2023 DCR-lite to drop - Small volume and no business impact by dropping it.
453896 | Linetek | Wang, Joanna | Notes | M0A0661-209(HP)N | 1 | NA | 1 |  |  |  |  | LUNU | M54454-201 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
453895 | Longwell | Wang, Joanna | Notes | 1011-0209 | 1 | NA | 1 |  |  |  |  | LUGR | M54454-101 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
82871 - C5 1.0m stkr Conventional Straight HF HE PWRCORD (Truly Linked Features: 53975)
517392 | ISHENG | Wang, Joanna | Notes | M57145-401 | 1 | NA |  |  |  | Unavailable |  | LZLT | M57145-401 | Dropped | 12/15/2023 DCR-lite to drop more ISHENG HF power cord from non-QC platforms.
517391 | Linetek | Wang, Joanna | Notes | K0A0661-263(HP)HF | 1 | NA | [5 empty] | LZLR | M57145-201 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
517389 | Longwell | Wang, Joanna | Notes | 1141-0054 | 1 | NA | [5 empty] | LZLE | M57145-101 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
75037 - C5 1.0m stkr Conventional Straight HF SWISS PWRCORD
453790 | ISHENG | Wang, Joanna | Notes | M54453-401 | 1 | NA | 1 |  |  | Unavailable |  | LVSE | M54453-401 | Dropped | 12/15/2023 DCR-lite to drop more ISHENG HF power cord from non-QC platforms.
453789 | Linetek | Wang, Joanna | Notes | K0A0661-261(HP)N | 1 | NA | 1 |  |  |  |  | LUNR | M54453-201 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
453788 | Longwell | Wang, Joanna | Notes | 1131-0058 | 1 | NA | 1 |  |  |  |  | LUGQ | M54453-101 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
82872 - C5 1.0m stkr Conventional Straight HF UK PWRCORD (Truly Linked Features: 53976)
517852 | ISHENG | Wang, Joanna | Notes | M57144-401 | 1 | NA |  |  |  | Unavailable |  | LZLQ | M57144-401 | Dropped | Inactive item.
517855 | Linetek | Wang, Joanna | Notes | P0A0661-208(HP)HF | 1 | NA | [5 empty] | LZLP | M57144-201 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
517854 | Longwell | Wang, Joanna | Notes | 1021-0177 | 1 | NA | [5 empty] | LZLD | M57144-101 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
50455 - C5 PWRCORD 1.0m stkr Premium ARGENTINA
247231 | Longwell | Wang, Joanna | Notes | PF8BFTKDA0AA033 | A | NA | A |  |  |  |  | GUSV | 401300-015 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
50465 - C5 PWRCORD 1.0m stkr Premium AUST
247239 | Longwell | Wang, Joanna | Notes | PL8B7TLDA0AA033 | A | NA | A |  |  |  |  | GUSB | 213356-018 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
50458 - C5 PWRCORD 1.0m stkr Premium BRZL
247232 | Longwell | Wang, Joanna | Notes | PF8BFNIDA0AA033 | A | NA | A |  |  |  |  | GURE | L03319-012 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
50461 - C5 PWRCORD 1.0m stkr Premium DEN
247235 | Longwell | Wang, Joanna | Notes | PF8BFG4DA0AA033 | A | NA | A |  |  |  |  | GURQ | 213353-018 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
50459 - C5 PWRCORD 1.0m stkr Premium EURO
402531 | Linetek | Wang, Joanna | Notes | M0A0661-205 | 2 | NA | 2 |  |  |  |  | JVVP | L03315-219 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
247233 | Longwell | Wang, Joanna | Notes | PF8BFC7DA0AA033 | A | NA | A |  |  |  |  | GURA | L03315-019 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
50462 - C5 PWRCORD 1.0m stkr Premium HE
247236 | Longwell | Wang, Joanna | Notes | PF8BFL9DA0AA033 | A | NA | A |  |  |  |  | GURC | L03317-013 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
50470 - C5 PWRCORD 1.0m stkr Premium INDIA
247244 | Longwell | Wang, Joanna | Notes | PV8A8RADA0AA033 | A | NA | A |  |  |  |  | GURD | L03318-013 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
50457 - C5 PWRCORD 1.0m stkr Premium ITL
247230 | Longwell | Wang, Joanna | Notes | PF8BFG5DA0AA033 | A | NA | A |  |  |  |  | GURL | 213352-018 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
50471 - C5 PWRCORD 1.0m stkr Premium JPN
247245 | Longwell | Wang, Joanna | Notes | PT8GTPYDM0AA033 | A | NA | A |  |  |  |  | GUSP | 349756-011 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
50467 - C5 PWRCORD 1.0m stkr Premium KOR
247241 | Longwell | Wang, Joanna | Notes | PF8K4C7D80AA033 | A | NA | A |  |  |  |  | GUSF | 267836-013 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
50456 - C5 PWRCORD 1.0m stkr Premium NA
402529 | Linetek | Wang, Joanna | Notes | F0A0661-203 | 3 | NA | 3 |  |  |  |  | JVVN | L03314-220 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
247229 | Longwell | Wang, Joanna | Notes | PH8BNETD90AA033 | A | NA | A |  |  |  |  | GUQV | L03314-020 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
50468 - C5 PWRCORD 1.0m stkr Premium PRC
247242 | Longwell | Wang, Joanna | Notes | P78B4TMD80AA033 | A | NA | A |  |  |  |  | GUZQ | 286497-018 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
50464 - C5 PWRCORD 1.0m stkr Premium SA
247238 | Longwell | Wang, Joanna | Notes | PF8BFM6DA0AA033 | A | NA | A |  |  |  |  | GUZR | 361240-012 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
50463 - C5 PWRCORD 1.0m stkr Premium SWISS
247237 | Longwell | Wang, Joanna | Notes | PF8BFG6DA0AA033 | A | NA | A |  |  |  |  | GURU | 213354-018 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
50466 - C5 PWRCORD 1.0m stkr Premium THAI
247240 | Longwell | Wang, Joanna | Notes | PF8BFETDA0AA033 | A | NA | A |  |  |  |  | GUZP | 285096-017 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
50469 - C5 PWRCORD 1.0m stkr Premium TW (Truly Linked Features: 13440)
279079 | Longwell | Wang, Joanna | Notes | PT8Y8IGIT0AA033 | 2 | NA | 2 |  |  |  |  | GURB | L03316-012 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
50460 - C5 PWRCORD 1.0m stkr Premium UK
402335 | Linetek | Wang, Joanna | Notes | P0A0661-205 | 1 | NA | 1 |  |  |  |  | JVVL | 213351-218 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
247234 | Longwell | Wang, Joanna | Notes | PF8BFVHDA0AA033 | A | NA | 2 |  |  |  |  | GURF | 213351-018 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
Processor
86799 - CPU Intel Core Ultra5 125H 4.50G 18 MB 14C 28W Intel - Meteor Lake-H (Truly Linked Features: 58631)
555244 | Intel | Chen, George | Notes | QQ807230556E/99CDJZ/SRMZ4 | C-0 | A06A4h |  | BFR/PVC |  |  |  | SLYU | N55465-N30 | Risk Release_BOM
86800 - CPU Intel Core Ultra5 135H vPro Enterprise 4.60G 18 MB 14C 28W Intel - Meteor Lake-H (Truly Linked Features: 58632)
555245 | Intel | Chen, George | Notes | Ultra5 135H | C-0 | A06A4h |  | BFR/PVC |  |  |  | SLYV | N55465-N40 | Risk Release_BOM
86798 - CPU Intel Core Ultra7 155H 4.80G 24 MB 16C 28W Intel - Meteor Lake-H (Truly Linked Features: 58630)
555243 | Intel | Chen, George | Notes | QQ807230556A/ 99CDJV/SRMZ1 | C-0 | A06A4h |  | BFR/PVC |  |  |  | SLYT | N55465-N20 | Risk Release_BOM
86797 - CPU Intel Core Ultra7 165H vPro Enterprise 5.00G 24 MB 16C 28W Intel - Meteor Lake-H (Truly Linked Features: 58629)
555242 | Intel | Chen, George | Notes | QQ8072305568/99CDJT/SRMZ3 | C-0 | A06A4h |  | BFR/PVC |  |  |  | SLYR | N55465-N10 | Risk Release_BOM
88144 - CPU Intel Core Ultra9 185H vPro Enterprise 5.10G 24 MB 16C 45W Intel - Meteor Lake-H (Truly Linked Features: 63110)
574001 | Intel | Taliaferro, Audra | Notes | QQ80723055C4/99CGJT/SRN23 | C-0 | A06A4h |  | BFR/PVC |  |  |  | TBZQ | N55465-N50 | Risk Release_BOM
Solid State Drive
74606 - 1TB PCIe-4x4 2280 NVME Self Encrypted OPAL2 Three Layer Cell Solid State Drive (Truly Linked Features: 45173,51645,51646,51647)
533770 | Kioxia | Cheng, Mark | Notes | KXG8AZNV1T02 | 1 | HPS1AP50 | Gen4x4 |  |  |  |  | QFEL | N12392-001 | QComplete | Added by DCR434506 and 434507 to support VW deal. Plan to qualify 3 suppliers due to low volumes for qual cost saving. If any urgent, we will request urgent qual back to system team later. Target QCompleted: 07/31 - done on 08/06/2024.
593525 | Micron | Cheng, Mark | Notes | MTFDKBA1T0TGD-1BK15ABHA | 1 | HPS0T50 | Gen4x4 |  |  |  |  | TFRV | N78348-001 | OOC | OPAL2 SSD was added by DCR to support WV deal. Plan to qualify top 3 suppliers due to low volume and qual cost saving. If any risk, CPM will bring qual request back to ST. Set OOC no qual plan.
629069 | Micron | Cheng, Mark | Notes | MTFDKBA1T0TGD-1BK15ABHA | 1 | HPS0T52 | Gen4x4 |  |  |  | HFCN | UHPD | N78348-002 | Investigating
580571 | Samsung (A1) | Cheng, Mark | Notes | MZVL21T0HCLR-00BH7 | Rev 0 | HPS4TGXH | Gen4x4 |  |  |  | HFCN | TFLN | M10829-004 | 09/08/2022 | in Aug. OOC
582499 | Western Digital | Cheng, Mark | Notes | SDCQNRY-1T00-1006 | A | HPS3T | Gen4x4 |  |  |  | HFCN | TFNA | M54706-003 | QComplete | Added by DCR434506 and 434507 to support VW deal. Plan to qualify 3 suppliers due to low volumes for qual cost saving. If any urgent, we will request urgent qual back to system team later. Target QCompleted: 07/31 - done on 08/06/2024.
87918 - 1TB PCIe-4x4 2280 NVMe Three Layer Cell China Solid State Drive (Truly Linked Features: 62645,63014,63015,63016)
571719 | Kioxia | Cheng, Mark | Notes | KXG80ZNV1T02 | 1 | HP01AP40 | Gen4x4 |  |  |  |  | QFEE | N12388-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
580580 | Samsung (A1) | Cheng, Mark | Notes | MZVL21T0HCLR-00BH1 | Rev0 | HPS4NGXH | Gen4x4 | BFR/PVC |  |  |  | TFLH | M10395-004 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
571556 | SK hynix | Cheng, Mark | Notes | HFS001TEJ9X101N | 0A | HPS1 | Gen4x4 | BFR/PVC |  |  |  | PZVV | N07861-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
571590 | Western Digital | Cheng, Mark | Notes | SDCPNRY-1T00-1006 | A | HPS2 | Gen4x4 |  |  |  |  | PVHD | M54702-002 | Dropped | 09/15/2023 DCR-lite to drop and replaced by new FW.
582827 | Western Digital | Cheng, Mark | Notes | SDCPNRY-1T00-1006 | A | HPS3 | Gen4x4 |  |  |  | HFCN | TFMP | M54702-003 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
74607 - 2TB PCIe-4x4 2280 NVME Self Encrypted OPAL2 Three Layer Cell Solid State Drive (Truly Linked Features: 45174,51648,51649,51650)
533773 | Kioxia | Cheng, Mark | Notes | KXG8AZNV2T04 | 1 | HPS1AP50 | Gen4x4 |  |  |  |  | QFEN | N12393-001 | QComplete | Added by DCR434506 and 434507 to support VW deal. Plan to qualify 3 suppliers due to low volumes for qual cost saving. If any urgent, we will request urgent qual back to system team later. Target QCompleted: 07/31 - done on 08/06/2024.
593529 | Micron | Cheng, Mark | Notes | MTFDKBA2T0TGD-1BK15ABHA | 1 | HPS0T50 | Gen4x4 | BFR/PVC |  |  |  | TFSA | N78349-001 | OOC | OPAL2 SSD was added by DCR to support WV deal. Plan to qualify top 3 suppliers due to low volume and qual cost saving. If any risk, CPM will bring qual request back to ST. Set OOC no qual plan.
629071 | Micron | Cheng, Mark | Notes | MTFDKBA2T0TGD-1BK15ABHA | 1 | HPS0T52 | Gen4x4 | BFR/PVC |  |  | HFCN | UHPF | N78349-002 | Investigating
580572 | Samsung (A1) | Cheng, Mark | Notes | MZVL22T0HBLB-00BH7 | Rev 0 | HPS4TGXG | Gen4x4 |  |  |  | HFCN | TFLP | M10830-004 | Planning
582501 | Western Digital | Cheng, Mark | Notes | SDCQNRZ-2T00-1006 | A | HPS3T | Gen4x4 |  |  |  | HFCN | TFNC | M54707-003 | 09/30/2024 | Sample ETA is late 08/30. Target QC: 09/30/2024.
87919 - 2TB PCIe-4x4 2280 NVMe Three Layer Cell China Solid State Drive (Truly Linked Features: 62646,63012,63013)
571721 | Kioxia | Cheng, Mark | Notes | KXG80ZNV2T04 | 1 | HP01AP40 | Gen4x4 |  |  |  |  | QFEF | N12389-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
580585 | Samsung (A1) | Cheng, Mark | Notes | MZVL22T0HBLB-00BH1 | Rev0 | HPS4NGXG | Gen4x4 | BFR/PVC |  |  |  | TFLK | M10396-004 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
571560 | SK hynix | Cheng, Mark | Notes | HFS002TEJ9X101N | 0A | HPS1 | Gen4x4 | BFR/PVC |  |  |  | PZWA | N07862-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
571585 | Western Digital | Cheng, Mark | Notes | SDCPNRZ-2T00-1006 | A | HPS2 | Gen4x4 |  |  |  |  | PVHE | M54703-002 | Dropped | 09/15/2023 DCR-lite to drop and replaced by new FW.
582829 | Western Digital | Cheng, Mark | Notes | SDCPNRZ-2T00-1006 | A | HPS3 | Gen4x4 |  |  |  | HFCN | TFMR | M54703-003 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
87920 - 4TB PCIe-4x4 2280 NVMe Three Layer Cell double-sided China Solid State Drive (Truly Linked Features: 62647,64998)
571880 | Kioxia | Cheng, Mark | Notes | KXG80ZN84T09 | 1 | HP01AP40 | Gen4x4 |  |  |  |  | QFEH | N12390-001 | QComplete | Qual result leveaged WW ver.
78539 - 4TB PCIe-4x4 2280 NVMe Three Layer Cell double-sided M.2 Solid State Drive (Truly Linked Features: 50854,51651,51652,51653)
528853 | Kioxia | Cheng, Mark | Notes | KXG80ZN84T09 | 1 | HP01AP40 | Gen4x4 |  |  |  |  | QFEH | N12390-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
554239 | Phison | Cheng, Mark | Notes | PSEIN004TA87MC0 | A | HPE23007 | Gen4x4 |  |  |  | HFCN | RSJB | M93208-003 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
87915 - 512GB PCIe 2280 NVMe Value China Solid State Drive (Truly Linked Features: 62642,63456,69815)
571689 | Kioxia | Cheng, Mark | Notes | KBG50ZNV512G | 01 | HP02AN00 | Gen4x4 |  |  |  |  | RXJN | M83990-002 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
612269 | Kioxia | Cheng, Mark | Notes | KBG60ZNV512G | 01 | HP02AX00 | Gen4x4 | BFR/PVC |  |  |  | THGR | N86403-001 | 09/06/2024 | 05202024 China veriosn , test report leverage from ID 610565.
571544 | Samsung (A1) | Cheng, Mark | Notes | MZVL8512HELU-00BH1 | Rev0 | HPS1NKXM | Gen4x4 | BFR/PVC |  |  |  | SFRT | N52404-001 | Dropped | 09/12/2023 DCR-lite to drop and replaced by new FW
582141 | Samsung (A1) | Cheng, Mark | Notes | MZVL8512HELU-00BH1 | Rev0 | HPS2NKXM | Gen4x4 | BFR/PVC |  |  | HFCN | SFRT | N52404-001 | Dropped | 12/01/2023 DCR-lite to drop and replace by new FW.
593528 | Samsung (A1) | Cheng, Mark | Notes | MZVL8512HELU-00BH1 | Rev0 | HPS3NKXM | Gen4x4 | BFR/PVC |  |  | HFCN | SFRT | N52404-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
571541 | SK hynix | Cheng, Mark | Notes | HFS512GEJ9X108N | 0A | HPS2 | Gen4x4 | BFR/PVC |  |  |  | RGYA | N29137-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
623484 | SK hynix | Cheng, Mark | Notes | HFS512GEM9X173N | 0A | HPS1 | Gen4x4 | BFR/PVC |  |  |  | TXRE | P06150-001 | 11/08/2024 | 08/15/2024 in Oct. 2024 OOC.
574461 | Solidigm | Cheng, Mark | Notes | SSDPFKNU512GZH | M41568-300 | HPS3 | Gen4x4 |  |  |  | HFCN | RGYC | N29139-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
580023 | Western Digital | Cheng, Mark | Notes | SDDPNQD-512G-2006 | A | HPS1 | Gen4x4 |  |  |  | HFCN | SWBH | N09761-0E1 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
605680 | Western Digital | Cheng, Mark | Notes | SDEPNSJ-512G-1006 | A | HPS1N5A | Gen4x4 |  |  |  |  | TKRE | N94050-001 | QComplete | 07032024 China Sku, test result leverega from WW verison.
74605 - 512GB PCIe-4x4 2280 NVME Self Encrypted OPAL2 Three Layer Cell Solid State Drive (Truly Linked Features: 45172,51476)
533769 | Kioxia | Cheng, Mark | Notes | KXG8AZNV512G | 1 | HPS1AP50 | Gen4x4 |  |  |  |  | QFEK | N12391-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
493442 | Micron | Cheng, Mark | Notes | MTFDKBA512TFH-1BC15ABHA | 1 | HPS0T43 | Gen4x4 |  |  |  |  | MDMF | M73973-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
593523 | Micron | Cheng, Mark | Notes | MTFDKBA512TGD-1BK15ABHA | 1 | HPS0T50 | Gen4x4 |  |  |  |  | TFRU | N78347-001 | QComplete | 06052024 Base on ODM test result.
629067 | Micron | Cheng, Mark | Notes | MTFDKBA512TGD-1BK15ABHA | 1 | HPS0T52 | Gen4x4 |  |  |  | HFCN | UHPB | N78347-002 | Investigating
580568 | Samsung (A1) | Cheng, Mark | Notes | MZVL2512HCJQ-00BH7 | Rev 0 | HPS4TGXH | Gen4x4 |  |  |  | HFCN | TFLL | M10398-004 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
490675 | Western Digital | Cheng, Mark | Notes | SDCQNRY-512G-1006 | A | HPS2T | Gen4x4 |  |  |  | HFCN | PVHH | M54705-002 | Dropped | 09/15/2023 DCR-lite to drop and replaced by new FW.
582498 | Western Digital | Cheng, Mark | Notes | SDCQNRY-512G-1006 | A | HPS3T | Gen4x4 |  |  |  | HFCN | TFMU | M54705-003 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
87917 - 512GB PCIe-4x4 2280 NVMe Three Layer Cell China Solid State Drive (Truly Linked Features: 62644,63017,63018,63019)
571881 | Kioxia | Cheng, Mark | Notes | KXG80ZNV512G | 1 | HP01AP40 | Gen4x4 |  |  |  |  | QFED | N12387-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
580574 | Samsung (A1) | Cheng, Mark | Notes | MZVL2512HCJQ-00BH1 | Rev0 | HPS4NGXH | Gen4x4 | BFR/PVC |  |  |  | TFLF | M10394-004 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
571552 | SK hynix | Cheng, Mark | Notes | HFS512GEJ9X101N | 0A | HPS1 | Gen4x4 | BFR/PVC |  |  |  | PZVU | N07860-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
571579 | Western Digital | Cheng, Mark | Notes | SDCPNRY-512G-1006 | A | HPS2 | Gen4x4 |  |  |  |  | PVHC | M54701-002 | Dropped | 09/15/2023 DCR-lite to drop and replaced by new FW.
582826 | Western Digital | Cheng, Mark | Notes | SDCPNRY-512G-1006 | A | HPS3 | Gen4x4 |  |  |  | HFCN | TFML | M54701-003 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
70733 - SSD 1TB 2280 PCIe-4x4 NVMe Three Layer Cell (Linked Features: 38694,45440,46429,51732,60297,70298)
532136 | Kioxia | Cheng, Mark | Notes | KXG80ZNV1T02 | 1 | HP01AP40 | Gen4x4 |  |  |  |  | QFEE | N12388-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
477963 | Micron | Cheng, Mark | Notes | MTFDKBA1T0TFH-1BC1AABHA | 1 | HPS0043 | Gen4x4 |  |  |  |  | MDMD | M73971-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
593518 | Micron | Cheng, Mark | Notes | MTFDKBA1T0TGD-1BK1AABHA | 1 | HPS0050 | Gen4x4 |  |  |  |  | TFRR | N78345-001 | QComplete | 06052024 Base on ODM test result
580345 | Samsung (A1) | Cheng, Mark | Notes | MZVL21T0HCLR-00BH1 | Rev 0 | HPS4NGXH | Gen4x4 | BFR/PVC |  |  | HFCN | TFLH | M10395-004 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
503163 | SK hynix | Cheng, Mark | Notes | HFS001TEJ9X101N | 0A | HPS1 | Gen4x4 |  |  |  |  | PZVV | N07861-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
490661 | Western Digital | Cheng, Mark | Notes | SDCPNRY-1T00-1006 | A | HPS2 | Gen4x4 |  |  |  | HFCN | PVHD | M54702-002 | Dropped | 09/15/2023 DCR-lite to drop and replaced by new FW.
582489 | Western Digital | Cheng, Mark | Notes | SDCPNRY-1T00-1006 | A | HPS3 | Gen4x4 |  |  |  | HFCN | TFMP | M54702-003 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
70734 - SSD 2TB 2280 PCIe-4x4 NVMe Three Layer Cell (Linked Features: 38695,45443,46430,53073,70299)
532137 | Kioxia | Cheng, Mark | Notes | KXG80ZNV2T04 | 1 | HP01AP40 | Gen4x4 |  |  |  |  | QFEF | N12389-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
477966 | Micron | Cheng, Mark | Notes | MTFDKBA2T0TFH-1BC1AABHA | 1 | HPS0043 | Gen4x4 |  |  |  |  | MDME | M73972-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
593521 | Micron | Cheng, Mark | Notes | MTFDKBA2T0TGD-1BK1AABHA | 1 | HPS0050 | Gen4x4 |  |  |  |  | TFRT | N78346-001 | QComplete | 08092024 Qcomplete base on Quanta's test result.
580536 | Samsung (A1) | Cheng, Mark | Notes | MZVL22T0HBLB-00BH1 | Rev 0 | HPS4NGXG | Gen4x4 |  |  |  | HFCN | TFLK | M10396-004 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
503164 | SK hynix | Cheng, Mark | Notes | HFS002TEJ9X101N | 0A | HPS1 | Gen4x4 |  |  |  |  | PZWA | N07862-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
490673 | Western Digital | Cheng, Mark | Notes | SDCPNRZ-2T00-1006 | A | HPS2 | Gen4x4 |  |  |  | HFCN | PVHE | M54703-002 | Dropped | 09/15/2023 DCR-lite to drop and replaced by new FW.
582495 | Western Digital | Cheng, Mark | Notes | SDCPNRZ-2T00-1006 | A | HPS3 | Gen4x4 |  |  |  | HFCN | TFMR | M54703-003 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
47268 - SSD 512GB 2280 PCIe NVMe Value (Linked Features: 8847,46524,46526,52069,52070,52071)
545519 | Kioxia | Cheng, Mark | Notes | KBG50ZNV512G | 01 | HP02AN00 | Gen4x4 | BFR/PVC |  |  |  | RXJN | M83990-002 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
610565 | Kioxia | Cheng, Mark | Notes | KBG60ZNV512G | 01 | HP02AX00 | Gen4x4 | BFR/PVC |  |  |  | THGR | N86403-001 | 09/06/2024 | 05202024 Plan in Aug 2024 OOC.
505412 | Micron | Cheng, Mark | Notes | MTFDKBA512QFM-1BD1AABHA | 1 | HPSQ041 | Gen4x4 |  |  |  |  | QHEQ | N13703-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
615896 | Micron | Cheng, Mark | Notes | MTFDKBA512QGN-1BN1AABHA | 1 | HPSQ050 | Gen4x4 |  |  |  |  | TXHT | P05899-001 | 09/06/2024 | Samples ETA in May, Aug OOC, 2024.
600294 | Phison | Cheng, Mark | Notes | PSENN512GA87FC0 | A | HPE51P00 | Gen4x4 |  |  |  |  | TPQD | N98620-001 | QComplete | 08052024 Qcomplete base on Quanta's test result.
571333 | Samsung (A1) | Cheng, Mark | Notes | MZVL8512HELU-00BH1 | Rev0 | HPS1NKXM | Gen4x4 | BFR/PVC |  |  |  | SFRT | N52404-001 | Dropped | 09/12/2023 DCR-Lite to drop and replace by new FW
581939 | Samsung (A1) | Cheng, Mark | Notes | MZVL8512HELU-00BH1 | Rev0 | HPS2NKXM | Gen4x4 | BFR/PVC |  |  | HFCN | SFRT | N52404-001 | Dropped | DCR lite on 12/1st/2023 to drop, Samsung two critical issues (Immunity of Ref. clocking noise and fix VPC mismatch issue) on FW= HPS2NKXM, Samsung released new FW= FW= HPS3NKXM for re-spin.
593522 | Samsung (A1) | Cheng, Mark | Notes | MZVL8512HELU-00BH1 | Rev0 | HPS3NKXM | Gen4x4 | BFR/PVC |  |  | HFCN | SFRT | N52404-001 | QComplete
553933 | SK hynix | Cheng, Mark | Notes | HFS512GEJ9X108N | 0A | HPS2 | Gen4x4 |  |  |  | HFCN | RGYA | N29137-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
623479 | SK hynix | Cheng, Mark | Notes | HFS512GEM9X173N | 0A | HPS1 | Gen4x4 | BFR/PVC |  |  |  | TXRE | P06150-001 | 11/08/2024 | 08/15/2024 in Oct. 2024 OOC.
565143 | Solidigm | Cheng, Mark | Notes | SSDPFKNU512GZH | M41568-300 | HPS3 | Gen4x4 |  |  |  | HFCN | RGYC | N29139-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
580013 | Western Digital | Cheng, Mark | Notes | SDDPNQD-512G-2006 | A | HPS1 | Gen4x4 |  |  |  | HFCN | SWBH | N09761-0E1 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
605674 | Western Digital | Cheng, Mark | Notes | SDEPNSJ-512G-1006 | A | HPS1N5A | Gen4x4 |  |  |  |  | TKRE | N94050-001 | QComplete | 07032024 test pass base on ODM's update.
70732 - SSD 512GB 2280 PCIe-4x4 NVMe Three Layer Cell (Linked Features: 38692,45691,46522,51731,60294,70297)
532130 | Kioxia | Cheng, Mark | Notes | KXG80ZNV512G | 1 | HP01AP40 | Gen4x4 |  |  |  |  | QFED | N12387-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
477960 | Micron | Cheng, Mark | Notes | MTFDKBA512TFH-1BC1AABHA | 1 | HPS0043 | Gen4x4 |  |  |  |  | MDMC | M73970-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
593512 | Micron | Cheng, Mark | Notes | MTFDKBA512TGD-1BK1AABHA | 1 | HPS0050 | Gen4x4 |  |  |  |  | TFRQ | N78344-001 | QComplete | 03/27/2024 Plan in July.2024 OOC.
580342 | Samsung (A1) | Cheng, Mark | Notes | MZVL2512HCJQ-00BH1 | Rev 0 | HPS4NGXH | Gen4x4 |  |  |  | HFCN | TFLF | M10394-004 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
503162 | SK hynix | Cheng, Mark | Notes | HFS512GEJ9X101N | 0A | HPS1 | Gen4x4 |  |  |  |  | PZVU | N07860-001 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
490652 | Western Digital | Cheng, Mark | Notes | SDCPNRY-512G-1006 | A | HPS2 | Gen4x4 |  |  |  | HFCN | PVHC | M54701-002 | Dropped | 09/15/2023 DCR-lite to drop and replaced by new FW.
582482 | Western Digital | Cheng, Mark | Notes | SDCPNRY-512G-1006 | A | HPS3 | Gen4x4 |  |  |  | HFCN | TFML | M54701-003 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
System Memory
87906 - 16GB (1x16GB) DDR5 5600 1.1v SODIMM China Memory (Truly Linked Features: 62633)
571055 | Kingston (K1) | Cheng, Mark | Notes | HP56S46BS8HA-16 | Hynix(A) | 2048Mx8 | China | BFR/PVC |  |  |  | TAYB | N20973-H81 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
579242 | Samsung (TH) | Cheng, Mark | Notes | M425R2GA3PB0-CWM | P | 2048Mx8 | China | BFR/PVC |  |  |  | RDHL | N20973-982 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
618374 | Samsung (TH) | Cheng, Mark | Notes | M425R2GA3EB0-CWM | E | 2048Mx8 | China | BFR/PVC |  |  |  | UDXF | N20973-983 | 10/11/2024 | 07/31/2024 in Sep 2024 OOC.
570883 | SK hynix | Cheng, Mark | Notes | HMCG78AGBSA | CP(A) | 2048Mx8 | China | BFR/PVC |  |  |  | QTWF | N20973-381 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
80622 - 16GB (1x16GB) DDR5 5600 1.1v SODIMM Memory (Truly Linked Features: 52551,59031)
513901 | Hynix (TG) | Cheng, Mark | Notes | HMCG78AGBSA | CP(A) | 2048Mx8 |  | BFR/PVC |  |  |  | QTWF | N20973-381 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
571011 | Kingston (K1) | Cheng, Mark | Notes | HP56S46BS8HA-16 | Hynix(A) | 2048Mx8 |  | BFR/PVC |  |  |  | TAYB | N20973-H81 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
576125 | Micron (TF) | Cheng, Mark | Notes | MTC8C1084S1SC56BD1 | Y52K/D | 2048Mx8 |  | BFR/PVC |  |  |  | TEHU | N20973-682 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
579240 | Samsung (TH) | Cheng, Mark | Notes | M425R2GA3PB0-CWM | P | 2048Mx8 |  | BFR/PVC |  |  |  | RDHL | N20973-982 | QComplete | my mistaken, return to previous status. QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
618373 | Samsung (TH) | Cheng, Mark | Notes | M425R2GA3EB0-CWM | E | 2048Mx8 | DC:2432 | BFR/PVC |  |  |  | UDXF | N20973-983 | 10/11/2024 | 7/31/2024 in Sep, 2024 OOC
87907 - 32GB (1x32GB) DDR5 5600 1.1v SODIMM China Memory (Truly Linked Features: 62634)
611928 | AData (L1) | Cheng, Mark | Notes | AO1V56WCTV2-BKYS | Hynix(A) | 2048Mx8 | China | BFR/PVC |  |  |  | TJVQ | N20974-B81 | 09/06/2024 | 05202024 China Veriosn, test result leverage from WW (ID 589682)
579245 | Samsung (TH) | Cheng, Mark | Notes | M425R4GA3PB0-CWM | P | 2048Mx8 | China | BFR/PVC |  |  |  | RDHP | N20974-982 | QComplete | Need Intel TA and WR PRC7 to fix issue. Align qual schedule with 1st OOC RTM 05/24. QCompleted based on sign off status. Need to do pilot run with BIOS 01.01.07.
618380 | Samsung (TH) | Cheng, Mark | Notes | M425R4GA3EB0-CWM | E | 2048Mx8 | China | BFR/PVC |  |  |  | UDXH | N20974-983 | 10/11/2024 | 07/31/2024 in Sep, 2024 OOC
570888 | SK hynix | Cheng, Mark | Notes | HMCG88AGBSA | CP(A) | 2048Mx8 | China | BFR/PVC |  |  |  | QTWH | N20974-381 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
80623 - 32GB (1x32GB) DDR5 5600 1.1v SODIMM Memory (Truly Linked Features: 52552,59032)
589682 | AData (L1) | Cheng, Mark | Notes | AO1V56WCTV2-BKYS | Hynix(A) | 2048Mx8 |  | BFR/PVC |  |  |  | TJVQ | N20974-B81 | 09/06/2024 | 03/27/2024 Plan in Aug. 2024 OOC bucket.
513905 | Hynix (TG) | Cheng, Mark | Notes | HMCG88AGBSA | CP(A) | 2048Mx8 |  | BFR/PVC |  |  |  | QTWH | N20974-381 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
579256 | Micron (TF) | Cheng, Mark | Notes | MTC16C2085S1SC56BD1 | Y52K/D | 2048Mx8 |  | BFR/PVC |  |  |  | TEHV | N20974-682 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
579244 | Samsung (TH) | Cheng, Mark | Notes | M425R4GA3PB0-CWM | P | 2048Mx8 |  | BFR/PVC |  |  |  | RDHP | N20974-982 | QComplete | Need Intel TA and WR PRC7 to fix issue. Align qual schedule with 1st OOC RTM 05/24. QCompleted based on sign off status. Need to do pilot run with BIOS 01.01.07.
618379 | Samsung (TH) | Cheng, Mark | Notes | M425R4GA3EB0-CWM | E | 2048Mx8 | DC:2432 | BFR/PVC |  |  |  | UDXH | N20974-983 | 10/11/2024 | 07/31/2024 in Sep. 2024 OOC bucket.
87905 - 8GB (1x8GB) DDR5 5600 1.1v SODIMM China Memory (Truly Linked Features: 62632)
571056 | Kingston (K1) | Cheng, Mark | Notes | HP56S46BS6HA-8 | Hynix(A) | 1024Mx16 | China | BFR/PVC |  |  |  | TAXV | N20972-H81 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
579248 | Samsung (TH) | Cheng, Mark | Notes | M425R1GB4PB0-CWM | P | 1024Mx16 | China | BFR/PVC |  |  |  | RDHH | N20972-982 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
570891 | SK hynix | Cheng, Mark | Notes | HMCG66AGBSA | CP(A) | 1024Mx16 | China | BFR/PVC |  |  |  | QTWE | N20972-381 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
80621 - 8GB (1x8GB) DDR5 5600 1.1v SODIMM Memory (Truly Linked Features: 52550,59030)
513920 | Hynix (TG) | Cheng, Mark | Notes | HMCG66AGBSA | CP(A) | 1024Mx16 |  | BFR/PVC |  |  |  | QTWE | N20972-381 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
571013 | Kingston (K1) | Cheng, Mark | Notes | HP56S46BS6HA-8 | Hynix(A) | 1024Mx16 |  | BFR/PVC |  |  |  | TAXV | N20972-H81 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/25/2024 to 02/08/2024 support Sub revA.
579253 | Micron (TF) | Cheng, Mark | Notes | MTC4C10163S1SC56BD1 | Y52K/D | 1024Mx16 |  | BFR/PVC |  |  |  | TEHT | N20972-682 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
579247 | Samsung (TH) | Cheng, Mark | Notes | M425R1GB4PB0-CWM | P | 1024Mx16 |  | BFR/PVC |  |  |  | RDHH | N20972-982 | QComplete | QCompleted align CF date 03/01/2024. Risk Release 01/23/2024 to 02/08/2024 support Sub revA.
Wired LAN
54377 - Ethernet Intel I219-LM 1GbE Vpro (Linked Features: 17409)
272262 | Intel | Fong, Agness | Notes | I219LM | 0.1 | 0.1 | [6 empty] | 819988-001 | Risk Release_BOM
66243 - Ethernet Intel I219-V 1GbE (Linked Features: 33055)
373429 | Intel | Fong, Agness | Notes | Intel I219V | MP | MP | [6 empty] | 823369-001 | Risk Release_BOM
78062 - HP USB 3.0 to Gigabit RJ45 Adapter G2 (Speedy 2) (Linked Features: 50154,50162,50164,71478)
615874 | BizLink | Freddy Huang | Notes | TPA-B003D | A | N/A | [6 empty] | M91115-001 | Risk Release_BOM
Wireless LAN
74792 - Intel Garfield Peak 2 AX211 Wi-Fi 6E +BT 5.3 M.2 2230 160MHz CNVi WW WLAN (Linked Features: 45363,52319,54476)
451613 | Intel | Yang, Daniel | Notes | AX211.NGWG.NV | WW | WW | [5 empty] | LTLL | M53266-001 | Risk Release_BOM
74791 - Intel Garfield Peak 2 AX211 Wi-Fi 6E +BT 5.3 M.2 2230 vPro 160MHz CNVi WW WLAN (Linked Features: 45362,51427,51428)
451612 | Intel | Yang, Daniel | Notes | AX211.NGWG | WW | WW | [5 empty] | LTLK | M53264-001 | Risk Release_BOM
Wireless LPWAN (Low Power)
89613 - WLPWAN Qualcomm Phantasm2 9205 LTE-M (CAT-M1 fSVC) (Linked Features: 65612)
588171 | Fibocom | Tan, Tony | Notes | 9205 | 9205NB | NB New Baseline |  |  |  | 11/01/2023 |  | THPN | N87326-001 | Risk Release_BOM
Wireless WAN
87570 - WWAN HP Kahlua 4000 4G LTE-Advanced Pro (Truly Linked Features: 61756)
568385 | Fibocom | Justin Chen | Notes | FM350-GL-16 | 1 | 1 | [5 empty] | TABV | N64677-001 | Risk Release_BOM